## Explorations
Exploration | Name | Description & Measurables | Findings | details | Requirement Reference
0 | Hello World | Make Sure I can print Hello World In Order to test that C++ is working | I determined that my c++,gcc compiler and makefile was working correctly I discovered that the -Wl,-subsystem,windows flag would prevent printing to console | Exploration\Hello_World
1 | Flat shader compilation | Create flat shader, make sure that it compiles | I discovered that I could create an abstraction of a flat shader, based on the shader I had used in another project, and it's source code related to initialising it, and using it
2 | Hello Triangle For Testing Renderer | Make sure that I can display a triangle on an SDL Window So that I can use this to build more complex polygons | I was able to render this, as seen in this screenshot
3 | SQL For Task Management |  | I was able to create an sqlite database, I was able to create the database, however I discoverer that it would be better to use a database only if there was a problem with using a spreedsheet for task management I discovered that it would not be too difficult to convert a CSV spreedsheet into a database | Exploration\SQLite_Sampler
4 | Excel for task management |  | I was able to create a spreedsheet that would contain the task and it's description. I discovered that this was a better way to store tasks I discovered that I was missing a requirements specification | This
5 | Get All Object Filed | Properly Understand how to get all object files using the pattern substring command | I was able to deduce what patsubst actually does. | Exploration\Get_All_Object_Files
6 | Build a libcester test | I want to build a working libtester test stub By using a makefile, since there are currently issues with doing this at the moment | It appears that I have to build libcester tests directly from it's cpp file, therefore I cannot compile it to an .o file first
7 | OpenGL with SDL |  | There is an OpenGL Flag that is required if opengl is being used in a SDL Windowc I was able to get a grey screen as I wanted
8 | Try Bigger tasks | Try working on tasks,which have multiple features, as it is likely to be easier to have less context switching between, analysis, design, implementation and testing(verification). Try a time frame of 1(Task) approximately 3 hours of work
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97

## Requirements
ID | Requirement | Specification | Category | Failure Cases | Status | Documents
0 | Creating a game like breakout | Given I Have <A major subset of the requirements satisfied>, then I should expect the breakout game to have been completed, Then I can deploy the game | System | The game crashes, The game does not load, The game frame rate gets below 30fps | Imprecise | Game Systems Document
1 | SDL headers and library file object | Given the ability to run C++ When I add these headers to a C++ source file or header file Then I will be able to successfully compile a program | Functional | Parts of the code base that require SDL fail to compile | Specified
2 | An Initialising an SDL Window | Given that SDL headers and library file object are able to be used in a program Then I can create an Abstraction of an SDL Window The SDL window is created with the specified properties | Functional | Window is not resizable even if it should be The Window initialises at the incorrect size The quit event does not occur when I press the close button Minimisation does not occur when I press the minimize button Maximisation it not toggled when I press the maximize button | Specified
3 | A File System Specification | Given that I am developing this Program on Windows 11 And the data that is stored on the disk is stored in a file system Then I should create a specification of the system structure for this project So that I can Add Source Code, Header files and documents to the file system | Documentation | There is a new file that needs to be added, but it does not fit the file definition. | Specified
4 | Initialisation of OpenGl in an SDL Window | Given that I have An SDL Window Abstraction When Intialise opengl with the sdl window And I Render a viewport at the same size as the window And I swap the window Then I am able to see a <colored> screen | Functional | The colour of the screen is different to what is specified | Specified
5 | ImGui Headers and source files | Given I have initialised an SDL Window I am able to display the demo Window in SDL 2 | Functional |  | Specified
6 | A Rectangle Abstraction | Given that a rectangle can be repesented in vector space And I have a vector math library Then I should be able to represent a Rectangle with a position and size to be used for Rectangle rendering and Rectangle intersection with another shape | Functional | If it was possible to define an invalid rectangle, for example it has a negative size (a rectangle should maintain it's invarient) | Specified
7 | Add Circle to the Circle Renderer | Given I have a circle abtraction And I can |  |  | Specified
8 | Set Circle Color of the Circle Renderer |  |  |  | Specified
9 | Clear The Circle Renderer |  |  |  | Specified
10 | Render Circles of the CircleRenderer | Given that OpenGl Has been integrated into the SDL Window And that I have Initialised the circle render Bind the buffers if the circle renderer Enable the vertex position and the color attribute array Draw the elements | Functional |  | Specified
11 |  |  |  |  | Specified
12 | A Renderable Quad Abstraction | Given an abstraction of a rectangle | Functional |  | Specified
13 |  |  |  |  | Specified
14 | PolygonAnColorShader |  | Functional |  | Specified
15 | Cursor with a position |  | Functional |  | Specified
16 | A Left button has be pressed | See a capsule rendered inside the Window | Functional |  | Specified
17 | A Right Button |  | Functional |  | Specified
18 | Button for moving left |  | Functional |  | Specified
19 | Button for moving right |  | Functional |  | Specified
20 | A Capsule Renderer |  | Functional |  | Specified
21 | A Circle Abstraction | Given that I am able to represent a circle in vector space And I have a vector math library Then I should be able to represent a circle with a position and a radius And this can be used in a renderer function | Functional |  | Specified
22 | A Circle Renderer |  |  |  | Specified
23 | A Rectangle Abstraction |  |  |  | Specified
24 | A Rectangle Renderer |  |  |  | Specified
25 | A Polygon Abstraction |  |  |  | Specified
26 | A Polygon Renderer |  |  |  | Specified
27 | All Shapes have Shape Rendering |  |  |  | Specified
28 | All Shapes has common abstraction |  |  |  | Specified
29 | CircleAndRectangle Intersection |  |  |  | Specified
30 | Get Point on Line Vector Nearest to another Point |  |  |  | Specified
31 | Get Point on Line Vector However cap points to line |  |  |  | Specified
32 | A Rectangle can intersect with a Rectangle | Given that I have a rectangle and another rectangle And that I can render the rectangles, for testing Either the two rectangles can be intersecting Or the two rectangles could not be intersecting Then this value can be used for any future context |  |  | Specified
33 | Circle And Polygon Intersection | Given that I have a circle and a polygon And that I could render a circles, for testing And that I can render a polygons, for testing Either the circle and the polygons intersect or The polygon and the circle does not intersect The the boolean result can be used in any future context |  |  | Specified
34 | Capsule And Polygon Intersection |  |  |  | Specified
35 | A Screen of pixel size |  |  |  | Specified
36 | A 2D Camera Representation |  |  |  | Specified
37 | BallIntersectsPaddle |  |  |  | Specified
38 | Ball Hits to hit a Left wall |  |  |  | Specified
39 | Ball Hits to hit a Right wall |  |  |  | Specified
40 | Ball Hits a ceiling |  |  |  | Specified
41 | Ball hits to hit a circular brick |  |  |  | Specified
42 | Ball hits to hit a rectangular brick |  |  |  | Specified
43 | Maintain a consistent Frame Rate |  |  |  | Specified
44 | Game maintains a constant speed regardless of frame rate |  |  |  | Specified
45 | Git and Github with ability to branch and see history | Given that I have set up a file system Then I can use version control to see the history of my code | Developer | Commits fail Unable to push or pull from github | Specified
46 | An imgui wrapper abstractuion | Given that I Have an SDL Window Abstraction And I Have Setup opengl in an SDL_Window When I create an ImguiWrapperAbstraction Then I can use this abstraction for further gui related functionality |  |  | Specified
47 | Make sure it is easy to extend functionality | Given I have created a new abstraction, to extend functionality Then I should decouple objects from Unnessessary composition So that I can minimise the amount of dependancies that exist between some classes | Developer | The refactored code, has different behavior, to the behavior that existed before
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97

## Tasks
task_id | task_name | task_category | task_status | task_details | requirement_reference
0 | File Setup | Development Process | Done | Tasks\File Setup | Requirements'!A5
1 | Git Setup | Development Process | Done | Tasks\Git Setup | Requirements'!A47
2 | Github Setup | Development Process | Done | Tasks\Github Setup | Requirements'!A47
3 | Focalboard For Tasks | Development Process | Done | Tasks\Setting Up Focalboard | None
4 | SDL_Window Example | Exploration | Done | Tasks\SDL Window Example | Requirements'!A4
5 | SDLEventWrapper | Refactor | Done | Tasks\SDL Event Wrapper | Requirements'!A4
6 | Create the Unit Test for the SDLWindowWrapper | Test Creation | Done | Tasks\Create A Unit Test for SDL Wrapper | Requirements'!A4
7 | Open Gl Setup | Exploration | Done | Tasks\OpenGl Setup | Requirements'!A6
8 | DearImgui Abstraction | Exploration | Done | Tasks\DearImGui Abstraction | Requirements'!A48
9 | Make SDLGLContextWrapper nd DearImGuiWrapper no longer be a composition of SDLWindowWrapper | Refactor | Implementing | Tasks\Decouple DearImGuiWrapper and Hello Triangle | Requirements'!A48
10
11
12 | Create a triangle that can be rendered in OpenGL | Development | Implementing
13 | Create ReadMe | Development Process | Todo
14 | Capsule Abstraction | Exploration | Todo
15 | Rectangle Abstraction | Exploration | Todo
16 | Github tags investigation | Exploration | Todo
17 | The closest point on an (infinite)line to other point function | Exploration | Todo
18 | The closest point on an (finite)line to other point function | Exploration | Todo
19 | Polygon Abstraction | Exploration | Todo
20 | Elipses Abstraction | Exploration | Todo
21
22 | Capsule Render | Exploration | Todo
23 | Circle Render | Exploration | Todo
24 | Rectangle Render | Exploration | Todo
25 | Elipses Render | Exploration | Todo
26 | Hello Triangle | Exploration | Todo
27 | In Development Docs Folder | Development Process | Todo
28 | A better system of Managing tasks | Development Process | Todo
29 | Decouple the Requirements from these tasks | Development Process | Todo
30 | Create Exloration folder | Development Process | Todo
31 | Explore SQLite | Development Process | Todo
32
33
34
35
32
33
34

## Bugs
Id | Name | Description | Assumed Cause | Cause and Correction Method
0 | Hello World not displaying in the console | For some reason the hello world program is not working, when I'm using a makefile | I assumed it was a build error Cause Bug | The -Wl,-subsystem,windows compiler flags actually supresses the console (in wrong context)
1 | Makefile Error | There is an error in the makefile | An incorrect file specified | Makefile Use Tabs instead of spaces
2 | Multiple Redefinition Errors |  | I assume that I might have included SDL2 twice since I still have the msys2 SDL2 headers | it could be to do with having SDL2 in both msys2 and in a random part of the system I reinstalled SDL2 using mysys2 continue using mysys2 for package management
3 | Undefined References to Win main |  | Something to do with the order of headers in the program | I forgot to add the main file, into the build exexutable makefile command (which is either main.cpp) or (same_as_executable_name.cpp)
4 | Undefined References in makefile | I have undefined references, I know the cause, but I should remember it |  | I forgot to add a command to build the object files
5 | Failing to build Libcester test | <command-line>: fatal error: .\tests\Unit\sdl_window_wrapper.test.cpp: No such file or directory | It appears that makefiles might not be able to recognise "./" in the command line for file names - Also for libcester unit testing, I must include .I in the makefile | Actually the issues were cause by not defining #define SDL_MAIN_HANDLED I will cause the program to crash if the SDL_MAIN_HANDLE is not defined when there is an SDLWindowWrapper SDL_MAIN_HANDLED
6 | multiple definition of |  |  | Usually cause by not having header guard on a header file And even when this is fixed, I will still need to delete one of the effected object file
7 | Something did not work even though I passes a pointer |  |  | In some circumstances I may need to use either a reference to a pointer or a pointer to a pointer
8
9
10
11
12
13
14
15
16
17
18